## Sheet1
CR-ID | Internal Change | Impact Analysis | SIQ-ID | SRS-ID | Design | Test Casess | Bug
CR-001 |  |  | SIQ-001 SIQ-010 | Req-Regs-001 | SQ_User_Regist_01 Car - Registration(flow chart) | Req-Regs-001 to Req-Regs-006
|  |  | SIQ-001 SIQ-009 | Req-Regs-002
|  |  | SIQ-009 | Req-Regs-003
|  |  | SIQ-001 | Req-Regs-004
Req-Regs-005
Req-Regs-006
|  |  | SIQ-001 | Req-Regs-007
CR-002 |  |  | SIQ-002 | Req-User-Log-001 | SQ_User_Login_02 Car - Login(flow chart) | Car-TC-login-001 Car-TC-login-003 Car-TC-login-004 Car-TC-login-007 Car-TC-login-009
|  |  | SIQ-002 | Req-User-Log-002
Req-User-Log-003
|  |  | SIQ-004 | Req-User-Log-004
CR-003 |  |  |  | Req-Res-001 | SQ_User_Reserve_06 Car - Reservation(flow chart) | Car-TC-UserHomePage-001 Car-TC-UserHomePage-002 Car-TC-UserHomePage-003
Req-Res-002
CR-004 |  |  | SIQ-002 | Req-Admin-log-001 | SQ_Admin_Login_01 Car - Login(flow chart) | Car-TC-login-002 Car-TC-login-005 Car-TC-login-006 Car-TC-login-008 Car-TC-login-010
|  |  | SIQ-002 | Req-Admin-log-002
|  |  | SIQ-004 | Req-Admin-log-003
|  |  | SIQ-004 | Req-Admin-log-004
|  |  | SIQ-005 SIQ-006 SIQ-008 | Req-Admin-log-005
CR-005 |  |  | SIQ-008 | Req-Add-Car-001 | SQ_Admin_AddCar_04 Car - Add Car (flow chart) | from Car-TC-AddCar-001 to Car-TC-AddCar-010
|  |  | SIQ-016 | Req-Add-Car-002
|  |  | SIQ-016 | Req-Add-Car-003
|  |  | SIQ-016 | Req-Add-Car-004
|  |  | SIQ-016 | Req-Add-Car-005
|  |  | SIQ-016 | Req-Add-Car-006
Req-Add-Car-007
CR-006 | CR_Des_updateCar_001 |  | SIQ-008 | Req-Update-Car-001 | SQ_Admin_UpdateCar_05 Car - Update Car (flow chart) | from Car-TC-UpdateCar-001 to Car-TC-UpdateCar-023 | from Car-Bug-UpdateCar-001 to Car-Bug-UpdateCar-004
|  |  | SIQ-008 | Req-Update-Car-002
|  |  | SIQ-016 | Req-Update-Car-003
|  |  | SIQ-016 | Req-Update-Car-004
|  |  | SIQ-016 | Req-Update-Car-005
|  |  | SIQ-016 | Req-Update-Car-006
Req-Update-Car-007
CR-007 |  |  | SIQ-008 | Req-Del-Car-001 | SQ_Admin_DeleteCar_06 Car - Delete Car (flow chart) | Car-TC-AdminHomePage-001 Car-TC-AdminHomePage-002 Car-TC-AdminHomePage-003 Car-TC-AdminHomePage-004 Car-TC-AdminHomePage-005
|  |  | SIQ-008 | Req-Del-Car-002
Req-Del-Car-003
Req-Del-Car-004
CR-008 | CR_Des_Search_002 |  |  | Remove search for a car feature | SQ_Admin_AddAdmin_07_ Delete Car (flow chart)
CR-009 |  | change_003 |  | Remove Add admin from Features according to the customer request | SQ_Admin_AddAdmin_02_ AddUser (flow chart)
CR-010 |  | change_003 |  | Remove search for a car feature | SQ_Admin_AddAdmin_03_ AddAdmin (flow chart)