## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [6 empty] | RISK MANAGEMENT LOG
Project Name: | Car-Booking System | [5 empty] | Project Name: | Car-Booking System
Project Manager Name: | Norhan Medhat | [5 empty] | Project Manager Name: | Norhan Medhat
Project Description: | This platform will host an enormous database of cars enabling the seller to advertise and market their cars and to help the buyer to search for their desired cars. | [5 empty] | Project Description: | This platform will host an enormous database of cars enabling the seller to advertise and market their cars and to help the buyer to search for their desired cars.
ID | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan | Current Status
RML_001 | High | Low | Yellow | Current project skill set may not be adequate to complete all project work. The current development team is not working on .Net MVC5 technology and the easiest way to develop the car-Booking system is implementing it with this technology, The organization will give the team the appropriate training in this new technology and give them enough time for trials and errors | If required skills for tyhis new technology are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | The new technology requires many pre-requists to learn it and there is time constraints | one week prior to implementation phase start date if no progress is identified with required skill set implement contingency plan. | Mitigation | Find internal resource that meets required skill set or train existing resources on web applications developments. | Change the plan to implement the system with a fiamiliar technology to the development team even if it will be more complex in implementation. | Open
RML_002 | Medium | Medium | Yellow | Current developers' number is limited if any developer has an emergency situation orquit suddenly for any reason the project timeline will be affected. | If any one from developers team left project schedule will be affected and deleivery time will be shifted. | Project Resources Budget Schedule | Required team members' numbers have to be assigned according to estimation with adding one or more members that may be unavailable. | Two weeks prior to scheduled start date if the number of team members is not identified with required skill set implement contingency plan. | Transfer | the risk will be transfered to Human Resource department to hire another employee as soon as possible to compensate the gap and the overtime load that the rest of team meber will carry instead. . | The team will work overtime or search for a freelancer to complete the job. | Open
RML_003 | Low | Low | Green | License for tools or OS may be expired and have to be renewed. | If the tools license is expired some teams can't continue their job and the project schedule may slip and possibly restrict the accomplishment of project goals. | Budget Schedule | The license end date has to be tracked by checking it or an alarm will appear. | A warning message of ending the license will appear to the team. | Avoidance | The IT support team will renew the licenses. | Using another open source tool. | Open
RML_004 | High | Medium | Red | Extra Budget will be paid to the trainers who will teach the development team the new technology and the budget may not be enough till the end of the project | If the budget is not enough for the project the development team will complete self learning with special trainer | Project Quality Budget | There implementation phase is more complex and the budget is lower than expected. | There were still 3 sessions to complete the course and the budget is lower than 15%. | Acceptance | Give the development team enough time for searching for the new technology with their own . | Complete the training cosurse and ask the finincial department to supply us with extra budget for improving team members skills | Open
RML_005 | High | Medium | Red | The wrong estimation of the project schedule, The project timeline is not enough to end the project. | if there was a deviation of project schedule the project won't be release with all the agreed featuresor will be delivered after dealine of delivery. | Schedule | Having technical debt or there is a delay in tasks delivery. | There were two weeks for delivery and all features were not closed yet. | Mitigation | The current team will work overtime to finish all features. | find someone internal that can help the team or searching for a freelancer to complete the job. | Open
RML_006 | Medium | Low | Green | Tools needed for the project are not available. | If required tools are not identified, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | Schedule approaches the required start date with no identification of required tools sets. | Two weeks prior to scheduled start date if no resource is identified with required tools set implement contingency plan. | Mitigation | Searching for alternative tools that can do the same job. | Looking for the root cause of the unavailability of this tool and trying to solve it. | Open

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources