## PMP
Version No. | Assigned To | Raised By | Date | Issue | Status | Approved By | Closed date
PMP_Review_V1.0 | Monica Norhan Eslam | Aya | 2022-04-14 | The assumption of the browsers the system will work on wasn't added | Closed | Aya | 2022-04-15
Version No. | Assigned To | Raised By | Date | Issue | Status | Approved By | Closed date
PMP-Review -V1.1 | Monica | Aya | 2022-04-27 | Part of WBS was wrong as search crieria for car was repeated (search by budget was reapeated 3 times) | Closed | Norhan | 2022-04-29
Version No. | Assigned To | Raised By | Date | Issue | Status | Approved By | Closed date
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | only one version of PMP the version was 9/4 while the file was updated more recently. | Closed | Monica | 2022-05-05
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | no revision history | Closed | Monica | 2022-05-05
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | Change control board needs to be identified before the changes | Closed | Monica | 2022-05-05
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | the configuration maanagment part needs to inlcude folder structure and what each folder will be used for. | Closed | Monica | 2022-05-05
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | no milestones unil the project end | Closed | Monica | 2022-05-05
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | the risk mangment document is very generic we need how to handle risk at your project | Closed | Monica | 2022-05-05
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | Change control board was missing one column which was Analysis SLA | Closed | Monica | 2022-05-06
PMP-Review -V1.2 | Monica | Aya | 2022-05-06 | Folder structure was wrong exchange highLevel Folder With low level folder | Closed | Monica | 2022-05-06
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-07 | Add Main change column in Revison history | Closed | Monica | 2022-05-07
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-07 | Remove assumptions from PMP as it took confirmation from customer | Closed | Monica | 2022-05-07
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-07 | Remove dates for uncompleted milestones in Project Schedule | Closed | Monica | 2022-05-07
PMP-Review -V1.3 | Aml | Eng.Amr Helal | 2022-05-13 | CI list need more details | Closed | Aml | 2022-05-20
PMP-Review -V1.3 | Aml | Eng.Mohamed Hassan | 2022-05-14 | Upated CM section to clarify the release version on GitHub (Vx) | Closed | Aml | 2022-05-20

## SRS
Version No. | Assigned To | Raised By | Date | Issue | Status | Approved By | Closed date
SRS-Review-V1.1 | Aya Basma | Monica Norhan | 2022-04-13 | The fuctionality that includes when adding new admin or user a random generated password and username should be sent on email is missing | Closed | Monica Norhan | 2022-04-14
SRS-Review-V1.1 | Aya Basma | Eslam | 2022-04-14 | Add the assumption that the admins username should be in a unique format to identify the admins when they login | Closed | Eslam | 2022-04-14
Version No. | Assigned To | Raised By | Date | Issue | Status | Approved By | Closed date
SRS-Review-V1.2 | Aya Basma | Eng.Mohmmed Hassan | 2022-04-23 | Change System numbering to be more specific like (1.1) | Closed | Monica | 2022-04-27
Version No. | Assigned To | Raised By | Date | Issue | Status | Approved By | Closed date
SRS-Review-V1.3 | Aya Basma | Eng.Amr Helal | 2022-05-05 | the rest of versions not existing only one is there | Closed | Monica | 2022-05-05
SRS-Review-V1.3 | Aya Basma | Eng.Amr Helal | 2022-05-05 | Errors while converting to PDF | Closed | Monica | 2022-05-05
SRS-Review-V1.3 | Aya Basma | Eng.Amr Helal | 2022-05-05 | Assumptions are in PMP and SRS needs to be in onle place | Closed | Monica | 2022-05-05
SRS-Review-V1.3 | Aya Basma | Eng.Amr Helal | 2022-04-05 | usecase is part of design not srs | Closed | Monica | 2022-05-05
SRS-Review-V1.3 | Aya Basma | Eng.Amr Helal | 2022-05-05 | requirements not clear and testable | Closed | Monica | 2022-05-05
SRS-Review-V1.3 | Aya Basma | Eng.Amr Helal | 2022-05-05 | tracibility is not clear | Closed | Monica | 2022-05-05
version No. | Assigned To | Raised By | Issue Date | Issues | Status | Approved By | Closed date
SRS-Review-v1.4 | Aya | Monica | 2022-05-05 | The error msg requirment must be in sperate requirmnet not part from other requirment | Closed | Monica | 2022-05-05
version No. | Assigned To | Raised By | Issue Date | Issues | Status | Approved By | Closed date
SRS-Review-v1.5 | Aya | Aml | 2022-05-11 | Review on Change the page design description moving the update button from under each car to the header next to add car in requirenments ( Req-Admin-log-004) (Req-Admin-log-004) and impacted SRS Sequance and wireframe | Closed | Aml | 2022-05-13
SRS-Review-v1.5 | Aya | Eng Amr | 2022-05-14 | Change update feature ( CR-006) desription to reflect the changes | Closed | Aml | 2022-05-17
SRS-Review-v1.5 | Aya | Eng Amr | 2022-05-14 | Identify priority measurement (High - Medium-Low) | Closed | Aml | 2022-05-17

## Design
Version No. | Assigned To | Raised By | Date | Issue | Status | Approved By | Closed date
Sequence Digram-Review-V1.1 | Norhan | Eng.Mohmmed Hassn | 2022-04-23 | make for each user seprate sequence diagram | Closed | Monica | 2022-04-27
Version No. | Assigned To | Raised By | Date | Issue | Status | Approved By | Closed date
Sequence Digram-Review-V1.2 | Norhan | Eng.Amr | 2022-05-05 | make ID name for each Requirement more clear | Closed | Monica | 2022-05-06
ERD-Review-V1.2 | Eslam | Eng.Amr | 2022-05-05 | choose to implement either ERD or ERD tables | Closed | Monica | 2022-05-06
Low Level design-V1.2 | Basma | Eng.Amr | 2022-05-05 | There is no low level design with details for system implementation | Closed | Monica | 2022-05-06
Tracibility-Review-V1.1 | Basma | Eng.Amr | 2022-05-07 | Missed Design Tracability | Closed | Monica | 2022-05-07
Version No. | Assigned To | Raised By | Date | Issue | Status | Approved By | Closed date
ERD-Review-V1.3 | Basma | Aml | 2022-05-13 | Update the ERD to follow the implementation | Closed | Aml | 2022-05-14
Sequence Digram-Review-V1.3 | Norhan | Aml | 2022-05-13 | Update the Sequence Digram to follow the implementation | Closed | Aml | 2022-05-14
Flow Chart-Review-V1.0 | Norhan | Aml | 2022-05-13 | Update the Flow Chart to follow the implementation | Closed | Aml | 2022-05-14
AdminHomePage-Review-v1.5 | Aya | Aml | 2022-05-11 | Review on Change the page design description moving the update button from under each car to the header next to add car in requirenments ( Req-Admin-log-004) (Req-Admin-log-004) and impacted SRS Sequance and wireframe | Closed | Aml | 2022-05-13
Tracibility-Review-v1.5 | Aya | Aml | 2022-05-13 | Update Tracibility to state the internal change (CR_Des_updateCar_001) to be tracked the change " Change the page design description moving the update button from under each car to the header" | Closed | Aml | 2022-05-14

## Coding
Admin Features
Version No. | Assigned To | Raised By | Date | Issue | Status | Approved By | Closed date | Comments
AddCar-Review-V1.0 | Nourhan | Eslam | 2022-05-12 | Choose File button was not similiar to the wireframe for this page | Closed | Eslam | 2022-05-14
AddCar-Review-V1.0 | Nourhan | Aml | 2022-05-13 | Image not loaded once navigate to/test ADD car page although it's added using Database | Closed | Aml | 2022-05-14
UpdateCar-Review-V1.0 | Nourhan | Basma | 2022-05-13 | No issue has been found | Closed | N/A | 2022-05-14
UpdateCar-Review-V1.0 | Nourhan | Aml | 2022-05-12 | Choose File button was not similiar to the wireframe for this page | Closed | Aml | 2022-05-14
DeleteCar-Review-V1.0 | Aya | Basma | 2022-05-13 | No issue has been found | Closed | N/A | 2022-05-14
AddUser_Review- V1.0 | Basma | Aml | 2022-05-13 | user page but written admin page needs to modify | Closed | Aml | 2022-05-13
AddAdmin_Review- V1.0 | Basma | Aml | 2022-05-13 | No issue has been found | Closed | N/A | 2022-05-14
Admin Home page-Review-V1.0 | Aya | Aml | 2022-05-13 | Price, id, brand,color of car labels were displayed in wrong place in the page | Closed | Aml | 2022-05-13
User Features
Version No. | Assigned To | Raised By | Date | Issue | Status | Approved By | Closed date
Registeration-Review- V1.0 | Eslam | Aml | 2022-05-13 | Registration Page need to add sending mail process to the user with valid username | Open
Login-Review- V1.0 | Eslam | Aya | 2022-05-13 | Login needs to be specified automatically if user navigate to the user home page if admin navigates to admin home page | Closed | Aya | 2022-05-14
Login-Review- V1.0 | Eslam | Aya | 2022-05-14 | User not login with his username | Closed | Aya | 2022-05-14
Search-Review- V1.0 | Aya | Aml | 2022-05-13 | Search feature not done to the end of the release and need to be finish by the next release Maximum | Closed | Aml | 2022-05-15 | Removed feature

## Immapc Analysis
Version No. | Assigned To | Raised By | Date | Issue | Status | Approved By | Closed date | Comments
V1 | Aya | Eng Amr | 14-5-2022 | In changing the project manager impact analysis table in actions column divide actions under time,cost or project | Closed | Aml | 17-5-2022
V1 | Aya | Eng Amr | 14-5-2022 | In changing the project manager impact analysis table in impact column first point be more specific in the extra time that will be needed as an impact on project manager change | Closed | Aml | 17-5-2022
V1 | Aya | Eng Amr | 14-5-2022 | In time pressure impact analysis table in actions column divide actions under time,cost or project | Closed | Aml | 17-5-2022
V1.1 | Basma | Aya | 18-5-2022 | In removing add admin and add users features impact analysis table (change_003) the impact on cost is not clear | Closed | Aya | 19-5-2022
V1.1 | Basma | Aya | 18-5-2022 | In removing add admin and add users features impact analysis table (change_003) the different actions that can be taken is not clear and need modification according to team discussions | Closed | Aya | 19-5-2022
V1.1 | Basma Galal | Aya Tarek | 18-5-2022 | In removing add admin and add users features impact analysis table (change_003) the chosen actions should be changed according to the updates of the actions that have been discussed with the team | Closed | Aya | 19-5-2022

## TC
Version No. | Assigned To | Raised By | Date | Issue | Status | Approved By | Closed date
UpdateCar_TC-Review-V1.0 | Norhan | Aml | 2022-05-23 | Need more coverage for Price, ID and image fields | Closed | Aml | 2022-05-24
UpdateCar_TC-Review-V1.0 | Norhan | Aml | 2022-05-23 | Need to raise a bug according to SRS there is a home page button in the admin update car page which is not exist | Closed | Aml | 2022-05-24
UpdateCar_TC-Review-V1.0 | Norhan | Aml | 2022-05-23 | Do not assume pop-Up message just stick to the only message in the SRS | Closed | Aml | 2022-05-24
UpdateCar_TC-Review-V1.0 | Norhan | Aml | 2022-05-23 | SRS didn't mention Image extension .. So I assume to the most common extentions (.TIFF,.JPEG,.jpg,.GIF,.png) | Closed | Aml | 2022-05-24
Admin_Home_Page_TC-Review-V1.0 | Eslam | Norhan | 2022-05-23 | When the admin entered his username and password, He is redirected to user home page | Closed | Norhan | 2022-05-23
User_Home_Page_TC-Review-V1.0 | Aya | Norhan | 2022-05-23 | No issues had been found | Closed | N/A
User_Home_Page_TC-Review-V1.0 | Norhan | Basma | 2022-05-25 | No issues had been found | Closed | N/A

## Progress
PMP | Open | 0 | SRS | Open | 0
| Closed | 15 |  | Closed | 13
| In Progress | 0 |  | In Progress | 0
| Need Approval | 0 |  | Need Approval | 0
| Total | 15 |  | Total | 13
Design | Open | 0 | Coding | Open | 1
| Closed | 10 |  | Closed | 11
| In Progress | 0 |  | In Progress | 0
| Need Approval | 0 |  | Need Approval | 0
| Total | 10 |  | Total | 12

## Option (hidden)
Open
Closed
In Progress
Need Approval