## Slide 1
2022
2022
Project Planning
Software Architecture
Software Implementation
Software Testing
Deployment
Today
Apr
May
5 days
Apr 9
PMP
Apr 15
0 days
Apr 9
Configuration Tool Setup
Apr 10
5 days
Apr 9
Apr 15
SRS
5 days
Apr 16
Apr 23
Design
10 days
Apr 26
May 9
Coding
4 days
May 10
May 13
Testing
5 days
May 14
May 20
UAT
1 day
May 23
Releasing