## Sheet1
ID | Quesition date | Asked by who | Question | Answer | Answer date | Answered by who | status
SIQ-001 | 2022-09-04 | Nourhan | What user needs for registeration? | user needs to register by email, password, mobile number and a unique username is sent on the mail for the user to login with next time. | 2022-09-04 | Amr | Closed
SIQ-002 | 2022-09-04 | Nourhan | What user and admin needs to login? | user need to login with both username and password. | 2022-09-04 | Amr | Closed
SIQ-003 | 2022-09-04 | Monica | what car features can user search for a car by? | user can search for car by brand, price and color | 2022-09-04 | Amr | Closed
SIQ-004 | 2022-09-04 | Monica | what car details in gui includes user page? | car details in gui must includes brand, price, color, image and ID. | 2022-09-04 | Amr | Closed
SIQ-005 | 2022-09-04 | Aya | Can admin add users? | admin can add users. | 2022-09-04 | Amr | Closed
SIQ-006 | 2022-09-04 | Aya | Can admin add other admins? | admin can add other admins. | 2022-09-04 | Amr | Closed
SIQ-007 | 2022-09-04 | Eslam | What the type of the system? | System must be Web app. | 2022-09-04 | Amr | Closed
SIQ-008 | 2022-09-04 | Eslam | What actions admin can do on a car? | Admin can add, update and delete car. | 2022-09-04 | Amr | Closed
SIQ-009 | 23/4/2022 | Basma | What is password validation? | No validation on password except valideating it is not empty field. | 23/4/2022 | Amr | Closed
SIQ-010 | 23/4/2022 | Basma | What is e-mail validation? | Only format validation on e-mail. | 23/4/2022 | Amr | Closed
SIQ-011 | 23/4/2022 | Eslam | What browsers the system will work on? | Browsers: Chrome, Firefox, and Edge. | 23/4/2022 | Amr | Closed
SIQ-012 | 23/4/2022 | Aya | What operating systems the system will work on? | Operating System: Windows 10, 11. | 23/4/2022 | Amr | Closed
SIQ-013 | 23/4/2022 | Nourhan | How to add new user or admin? | When adding new user or admin by the admin through entering the email the system shall generate random password and username and send them through the email. | 23/4/2022 | Amr | Closed
SIQ-014 | 23/4/2022 | Eslam | How to identify the admins? | When generating random usernames, the system shall give admin username specific format so it can be identified as a admin. | 23/4/2022 | Amr | Closed
SIQ-015 | 23/4/2022 | Aya | what car details in gui includes Admin page? | car details in gui must includes brand, price, color, image and ID and buttons for add new admin , user update , delete,add car . | 2022-09-04 | Amr | Closed
SIQ-016 | 23/24/2022 | Basma | what is the GUI of update and Add car page? | the admin will be able to choose the brand ,color from dropdown list ,put the price and upload image .