## PMP
version No. | Assigned To | Raised By | Date | Issue | status | Approved By | Closed date
PMP_Review_V1.0 | Monica Norhan Eslam | Aya | 2022-04-14 | The assumption of the browsers the system will work on wasn't added | Closed | Aya | 2022-04-15
version No. | Assigned To | Raised By | Date | Issue | status | Approved By | Closed date
PMP-Review -V1.1 | Monica | Aya | 2022-04-27 | Part of WBS was wrong as search crieria for car was repeated (search by budget was reapeated 3 times) | Closed | Norhan | 2022-04-29
version No. | Assigned To | Raised By | Date | Issue | status | Approved By | Closed date
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | only one version of PMP the version was 9/4 while the file was updated more recently. | Closed | Monica | 2022-05-05
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | no revision history | Closed | Monica | 2022-05-05
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | Change control board needs to be identified before the changes | Closed | Monica | 2022-05-05
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | the configuration maanagment part needs to inlcude folder structure and what each folder will be used for. | Closed | Monica | 2022-05-05
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | no milestones unil the project end | Closed | Monica | 2022-05-05
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | the risk mangment document is very generic we need how to handle risk at your project | Closed | Monica | 2022-05-05
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-05 | Change control board was missing one column which was Analysis SLA | Closed | Monica | 2022-05-06
PMP-Review -V1.2 | Monica | Aya | 2022-05-06 | Folder structure was wrong exchange highLevel Folder With low level folder | Closed | Monica | 2022-05-06
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-07 | Add Main change column in Revison history | Closed | Monica | 2022-05-07
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-07 | Remove assumptions from PMP as it took confirmation from customer | Closed | Monica | 2022-05-07
PMP-Review -V1.2 | Monica | Eng.Amr Helal | 2022-05-07 | Remove dates for uncompleted milestones in Project Schedule | Closed | Monica | 2022-05-07

## Options (hidden)
Open
Close

## SRS
version No. | Assigned To | Raised By | Issue Date | Issues | Status | Approved By | Closed date
SRS-Review-V1.1 | Aya Basma | Monica Norhan | 2022-04-13 | The fuctionality that includes when adding new admin or user a random generated password and username should be sent on email is missing | Closed | Monica Norhan | 2022-04-14
SRS-Review-V1.1 | Aya Basma | Eslam | 2022-04-14 | Add the assumption that the admins username should be in a unique format to identify the admins when they login | Closed | Eslam | 2022-04-14
version No. | Assigned To | Raised By | Issue Date | Issues | Status | Approved By | Closed date
SRS-Review-V1.2 | Aya Basma | Eng.Mohmmed Hassan | 2022-04-23 | Change System numbering to be more specific like (1.1) | Closed | Monica | 2022-04-27
version No. | Assigned To | Raised By | Issue Date | Issues | Status | Approved By | Closed date
SRS-Review-V1.3 | Aya Basma | Eng.Amr Helal | 2022-05-05 | the rest of versions not existing only one is there | Closed | Monica | 2022-05-05
SRS-Review-V1.3 | Aya Basma | Eng.Amr Helal | 2022-05-05 | Errors while converting to PDF | Closed | Monica | 2022-05-05
SRS-Review-V1.3 | Aya Basma | Eng.Amr Helal | 2022-05-05 | Assumptions are in PMP and SRS needs to be in onle place | Closed | Monica | 2022-05-05
SRS-Review-V1.3 | Aya Basma | Eng.Amr Helal | 2022-04-05 | usecase is part of design not srs | Closed | Monica | 2022-05-05
SRS-Review-V1.3 | Aya Basma | Eng.Amr Helal | 2022-05-05 | requirements not clear and testable | Closed | Monica | 2022-05-05
SRS-Review-V1.3 | Aya Basma | Eng.Amr Helal | 2022-05-05 | tracibility is not clear | Closed | Monica | 2022-05-05
version No. | Assigned To | Raised By | Issue Date | Issues | Status | Approved By | Closed date
SRS-Review-v1.4 | Aya | Monica | 2022-05-05 | The error msg requirment must be in sperate requirmnet not part from other requirment | Closed | Monica | 2022-05-05

## Design
version No. | Assigned To | Raised By | Date | Issue | status | Approved By | Closed date
Sequence Digram-Review-V1.1 | Norhan | Eng.Mohmmed Hassn | 2022-04-23 | make for each user seprate sequence diagram | Closed | Monica | 2022-04-27
version No. | Assigned To | Raised By | Date | Issue | status | Approved By | Closed date
Sequence Digram-Review-V1.2 | Norhan | Eng.Amr | 2022-05-05 | make ID name for each Requirement more clear | Closed | Monica | 2022-05-06
ERD-Review-V1.2 | Eslam | Eng.Amr | 2022-05-05 | choose to implement either ERD or ERD tables | Closed | Monica | 2022-05-06
Low Level design-V1.2 | Basma | Eng.Amr | 2022-05-05 | There is no low level design with details for system implementation | Closed | Monica | 2022-05-06