## Slide 1
2022
2022
Project Planning
Software Architecture
Software Implementation
Releasing
Fixing Phase
Today
Apr
May
5 days
Apr 9
PMP
Apr 15
1 day
Apr 9
Configuration Tool Setup
Apr 11
5 days
Apr 9
Apr 15
SRS
2 days
Apr 23
Apr 26
Sequence Diagram
38 days
Coding & DB Initiation & Testing
1 day
Deployment
Jun
3 days
Apr 19
WireFrame
Apr 21
5 days
Apr 24
Make Traceability Matrix
Apr 29
1 day
Apr 25
Edititng SIQ
2 days
Apr 24
Editing SRS
Apr 26
May 7
Jun 30
Jun 29
To be determined.

## Slide 2
2022
2022
Authentication
Admin Features
User Features
Today
Day 1
2
3
4
5
6
7
8
9
10
5 days
May 7
May 14
Registration Page
4 days
May 10
May 14
Login Page
2 days
May 5
May 6
Admin Home Page
2 days
May 6
May 9
Add Admin
3 days
May 11
May 13
Add User
5 days
May 9
May 13
Add Car
4 days
May 10
May 13
Delete Car
2 days
May 12
May 13
Update Car
1 day
May 6
May 8
User Home Page
5 days
May 9
May 13
Car Reservation
To be determined.